## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: Wikiviewer
ΠΛΗ 24 |  |  |  |  | Legend: | XL |  |  |  |  | L |  |  |  |  | M |  |  |  |  | S |  |  |  |  | XS
PM CHRISTOS ANDRIOPOULOS
Project start date: | 2026-01-25 |  |  |  |  | January | [6 empty] | February | [27 empty] | March
Scrolling increment: | 5 | time axis 2026-01-30 to 2026-03-26
ACTIVITY CODE | Category | Assigned to | Progress | Start | Days | time axis 2026-01-30 to 2026-03-26
SPRINT 1
PR.1 | XL | ALL TM | 100% | 2026-02-01 | 1
PR.2 | XL | ALL TM | 100% | 2026-02-02 | 1
PR.3 | XL | ALL TM | 100% | 2026-02-03 | 1
PR.4 | XL | ALL TM | 80% | 2026-02-05 | 5
PR.5 | XL | ALL TM | 75% | 2026-02-07 | 5
R1 | S | C. ANDRIOPOULOS | 100% | 2026-02-12 | 1
SPRINT 2
PR.4 / PR.5 | XL | ALL TM | 100% | 2026-02-16 | 2
R2.A | XL | T. DEMISARLIS | 100% | 2026-02-17 | 1
R2.B | XL | T. DEMISARLIS | 100% | 2026-02-18 | 2
R2.C | M | C. ANDRIOPOULOS | 100% | 2026-02-16 | 1
R2.D | XL | I. KARAGIANNIS | 100% | 2026-02-18 | 2
R2.E | XL | I. KARAGIANNIS | 100% | 2026-02-19 | 1
R2.F | XL | T. DEMISARLIS | 100% | 2026-02-20 | 1
R3 | L | T. DEMISARLIS | 100% | 2026-02-21 | 1
R4.A | M | C. ANDRIOPOULOS | 100% | 2026-02-21 | 1
R4.B | M | T. DEMISARLIS | 100% | 2026-02-22 | 2
R4.C | M | I. KARAGIANNIS | 100% | 2026-02-23 | 1
SPRINT 3
R5.A | XL | T. DEMISARLIS | 100% | 2026-02-25 | 1
R5.B | L | I. KARAGIANNIS | 100% | 2026-02-25 | 1
R5.C | M | C. ANDRIOPOULOS | 100% | 2026-02-25 | 1
R6.A | M | C. ANDRIOPOULOS | 100% | 2026-02-28 | 1
R6.B | S | I. KARAGIANNIS | 100% | 2026-03-01 | 1
R6.C | M | T. DEMISARLIS | 100% | 2026-03-01 | 2
MISC 1 | S | C. ANDRIOPOULOS | 100% | 2026-03-02 | 1
MISC 2 | M | C. ANDRIOPOULOS | 100% | 2026-03-02 | 1
MISC 3 | M | T. DEMISARLIS - C. ANDRIOPOULOS | 100% | 2026-03-02 | 1
MISC 4 | L | ALL TM | 100% | 2026-03-03 | 1
MISC 5 | XS | C. ANDRIOPOULOS | 100% | 2026-03-03 | 1
MISC 6 | XL | ALL TM | 100% | 2026-02-27 | 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2026-02-26 |  |  |  |  | March | [34 empty] | April
Scrolling increment: | 5 | time axis 2026-03-03 to 2026-04-27
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
TITLE 1
Task 1 | Goal | Name | 25% | 2026-02-26 | 3
Task 2 | Milestone |  |  | 2026-03-03 | 1 | bar: T
Task 3 | Low Risk |  | 50% | 2026-02-23 | 10
Task 4 | Milestone |  |  | 2026-03-18 | 1 | bar: W
Task 5 | Med Risk |  | 10% | 2026-03-04 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2026-03-04 | 13
Task 2 | On Track |  | 50% | 2026-03-06 | 9
Task 3 | Low Risk |  | 33% | 2026-03-11 | 11
Task 4 | Milestone |  |  | 2026-03-13 | 1 | bar: F
Task 5 |  |  |  | 2026-03-14 | 24
TITLE 3
Task 1 | On Track |  |  | 2026-03-13 | 4
Task 2 | Med Risk |  |  | 2026-03-16 | 14
Task 3 | On Track |  |  | 2026-03-31 | 6
Task 4 | Goal |  |  | 2026-04-04 | 3 | S: 2; S: 2; M: 2
Task 5 | Low Risk |  |  | 2026-03-04 | 19
TITLE 4
Task 1 |  |  |  | 2026-04-07 | 15
Task 2 |  |  |  | 2026-04-21 | 5
Task 3 | Milestone |  |  | 2026-06-02 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2026-02-26 |  |  |  |  | March | [34 empty] | April
Scrolling increment: | 5 | time axis 2026-03-03 to 2026-04-27
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-03-03 to 2026-04-27
TITLE 1
Task 1 | Goal | Name | 25% | 2026-02-26 | 3
Task 2 | Milestone |  |  | 2026-03-03 | 1 | bar: 2026-03-03
Task 3 | Low Risk |  | 50% | 2026-02-23 | 10
Task 4 | Milestone |  |  | 2026-03-18 | 1 | bar: 2026-03-18
Task 5 | Med Risk |  | 10% | 2026-03-04 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2026-03-04 | 13
Task 2 | On Track |  | 50% | 2026-03-06 | 9
Task 3 | Low Risk |  | 33% | 2026-03-11 | 11
Task 4 | Milestone |  |  | 2026-03-13 | 1 | bar: 2026-03-13
Task 5 |  |  |  | 2026-03-14 | 24
TITLE 3
Task 1 | On Track |  |  | 2026-03-13 | 4
Task 2 | Med Risk |  |  | 2026-03-16 | 14
Task 3 | On Track |  |  | 2026-03-31 | 6
Task 4 | Goal |  |  | 2026-04-04 | 3 | 2026-04-04: 2; 2026-04-05: 2; 2026-04-06: 2
Task 5 | Low Risk |  |  | 2026-03-04 | 19
TITLE 4
Task 1 |  |  |  | 2026-04-07 | 15
Task 2 |  |  |  | 2026-04-21 | 5
Task 3 | Milestone |  |  | 2026-06-02 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one